## Tasks
Task Name | Charles | Adam | Shawn | Mohammed | Aya | Kellie | Conrad | Kevin | Lori | Vardan
Contract Signed
Contract Form Completed
Customer Integration Requirements
Contract Form
Details Form
Contract Form Completed
Details Form Completed
Integration
Request Customer Integration Requirement from Partner | [8 empty] | 30
Schedule the Kick Off | [8 empty] | 30
Submit DevOps ticket: Create the site | [8 empty] | 30
Create the site(s)
Host Kick Off Session | [8 empty] | 60
Send App Server Specs and Scripts to Partner | [8 empty] | 30
Partner verifies that the scripts are installed
Send Firewall and WhiteList information to Customer | [8 empty] | 30
Validate Firewall is Open | [8 empty] | 30
Validate messages are working | [8 empty] | 30
Validate SBO Transactoin Notification was properly modified (Saltbox and SLSync Only)
Request Access Details to Customer's SAP | [8 empty] | 30
Customer to Provide SAP Access
Add Customer's SAP details to Bitwarden | [8 empty] | 30
Blueprint
Schedule Configuration (BluePrint) meeting | [8 empty] | 30
Host Configuration (BluePrint) meeting | [8 empty] | 90
Blueprint is countersigned
Send countersigned Blueprint to Implementation teams (FP & SAP) | [8 empty] | 30
Configuration
Create and send Customer login information | [8 empty] | 30
Send Checklist to Customer | [8 empty] | 30
Additional Field Mapping
Configure Site - General | [8 empty] | 90
Configure Site - Pricing | [8 empty] | 60
Configure Site - Shipping | [8 empty] | 60
Configure Site - Taxes | [8 empty] | 60
Training
Schedule 2 Training Sessions: FocusPoint & Data Transfer Workbench | [8 empty] | 30
Send Customer Training Files | [8 empty] | 30
FocusPoint Configuration Training Session #1 | [8 empty] | 90
Request Customer to web enable items from SAP Interface
Send Customer catagory excel file | [8 empty] | 30
Data Transfer Workbench Training Session #2 | [8 empty] | 90
Schedule FocusPoint Training Session | [8 empty] | 30
FocusPoint Training Session | [8 empty] | 90
Website Design
Customer to add Categories
Schedule Design Session | [8 empty] | 30
Host Design Session | [8 empty] | 90
Customer to Complete Checklist
Complete Customer Design
Customer Site Design (Optional)
Data
Customer to Complete Data
Schedule Status Meetings | [8 empty] | 30
Schedule Follow up training session (Contract dependent) | [8 empty] | 90
Schedule status calls based on Customers availability | [8 empty] | 30
Quality Assurance Sign Off (Internal) Testing
Review - Search Product | [8 empty] | 60
Review - Order Process | [8 empty] | 120
Review - Links | [8 empty] | 60
Review - Banners and Logos | [8 empty] | 30
Review - Customer roles | [8 empty] | 60
Review - Special Requests: Pricing, Taxes, Shipping, etc. | [8 empty] | 120
User Acceptance Testing
Customer to Complete UAT in Testing
Complete UAT follow-up | [8 empty] | 30
Production
Install Integration Scripts in Production
Load DTW to Production
Sync Test Data with Production
Refresh Database with Test Data
Quality Assurance Sign Off (Internal) Production
Review - Search Product | [8 empty] | 30
Review - Order Process | [8 empty] | 60
Review - Links | [8 empty] | 30
Review - Banners and Logos | [8 empty] | 30
Review - Customer roles | [8 empty] | 30
Review - Special Requests: Pricing, Taxes, Shipping, etc. | [8 empty] | 60
UAT in Production
Customer to Complete UAT in Production
Complete UAT follow-up | [8 empty] | 30
Go Live Checklist
Schedule Go-Live Checklist meeting | [8 empty] | 30
Host Go-Live Checklist meeting | [8 empty] | 30
Go Live
Final Site Validation
Remove test data from Production site
Install SSL Certificate
Domain Name
Final Design Items - Flavicon, etc.
Go Live Switch Domain
Set up on helpdesk and give helpdesk information
Schedule follow up sessions for 1 month out | [8 empty] | 30
Custom Development (Optional per customer)
Gather full requirements
Development
FP Testing
Quality Assurance
Request Customer Feedback
Return to Development (if needed)